## Dashboard Summary
Communications Plan Measurement & Effectiveness Framework
Internal Comms Plan — Leadership Strategy Rollout
Reporting Period: March 2026
AUDIENCE HEALTH SUMMARY
Audience Group | Overall Health Score | Key Risk | Priority Action
Corporate Employees | To be measured | Low engagement with strategic narrative | Launch targeted intranet content
Frontline / Operations Employees | To be measured | Disconnect between corporate messaging and daily experience | Manager-led sessions with local context
People Managers | To be measured | Burnout and insufficient preparation | Immediate coaching investment
Note: Health scores will be populated after first 30-day measurement cycle. See 'Success Metrics' sheet for full KPI tracking.

## Success Metrics
Success Metrics — Communications Effectiveness Measurement
Metric ID | Metric Name | Description | Audience Group | Data Source | Baseline (Current) | Target (30 Days) | Target (90 Days) | Measurement Frequency | Owner
M-001 | Email Open Rate — Corporate | Percentage of corporate employees who open leadership email communications | Corporate | Email platform analytics (e.g., Outlook Insights) | 42% | 60% | 70% | Per send | Comms Lead
M-002 | Email Read Rate — Corporate | Percentage of corporate employees who read >50% of email content | Corporate | Email platform analytics | 28% | 45% | 60% | Per send | Comms Lead
M-003 | Email Open Rate — Frontline | Percentage of frontline employees who open communications via email or app | Frontline | Email / workforce app analytics | 25% | 45% | 60% | Per send | Ops Comms
M-004 | Email Read Rate — Frontline | Percentage of frontline employees who fully read communications | Frontline | Email / workforce app analytics | 15% | 35% | 50% | Per send | Ops Comms
M-005 | Intranet Hub Page Views | Total page views on the dedicated leadership strategy intranet hub | All | Intranet analytics (SharePoint / Confluence) | 0 (new) | 2,500 | 5,000 | Weekly | Digital Comms
M-006 | Intranet Hub Unique Visitors | Unique employee visitors to the leadership strategy intranet hub | All | Intranet analytics | 0 (new) | 800 | 1,500 | Weekly | Digital Comms
M-007 | FAQ Page Engagement Rate | Percentage of hub visitors who click into the FAQ section | All | Intranet analytics | N/A | 30% | 50% | Weekly | Comms Lead
M-008 | FAQ Page Average Time on Page | Average time employees spend reading the FAQ page (signals depth of engagement) | All | Intranet analytics | N/A | 2 min | 3 min | Weekly | Digital Comms
M-009 | Manager Meeting Completion Rate | Percentage of team meetings completed by managers within the rollout window | Managers | Manager reporting / HR system | N/A | 80% by Day 7 | 95% by Day 30 | Weekly | HR Lead
M-010 | Employee Sentiment — Understanding | Pulse survey score: employees report understanding the strategic direction (1–10 scale) | All | Pulse survey platform | Baseline to be set at launch | 6.5 / 10 | 7.5 / 10 | Bi-weekly | HR Lead
M-011 | Employee Sentiment — Confidence | Pulse survey score: employees feel confident about their role in the strategy | All | Pulse survey platform | Baseline to be set at launch | 6.0 / 10 | 7.0 / 10 | Bi-weekly | HR Lead
M-012 | Employee Sentiment — Trust in Leadership | Pulse survey score: employees trust leadership communication (1–10 scale) | All | Pulse survey platform | Baseline to be set at launch | 6.0 / 10 | 7.5 / 10 | Monthly | CHRO
M-013 | Manager Confidence Score | Managers self-report confidence in delivering key strategic messages (1–10 scale) | Managers | Manager feedback form / pulse | Baseline to be set at kickoff | 7.0 / 10 | 8.5 / 10 | Bi-weekly | HR Lead
M-014 | Voluntary Attrition Rate Change | Month-over-month change in voluntary attrition versus pre-rollout baseline | All | HRIS (Workday / SAP SuccessFactors) | Current monthly attrition rate | +/- 0% vs baseline | No increase vs baseline | Monthly | CHRO
M-015 | Questions Submitted via Feedback Channels | Volume and themes of questions submitted through 'Ask Leadership' or feedback tools | All | Intranet / email submission tool | 0 (new channel) | 50 questions | 100 questions | Weekly | Comms Lead
M-016 | Manager Coaching Program Enrollment | Percentage of people managers enrolled in the leadership messaging coaching program | Managers | LMS / HR training records | 0% | 70% | 100% | Weekly | L&D Lead
M-017 | eNPS Shift (Employee Net Promoter Score) | Change in eNPS score versus pre-rollout benchmark — measures employee advocacy | All | eNPS pulse survey | Pre-rollout score to be captured | +5 points | +10 points | Quarterly | CHRO
M-018 | Internal Search Trends | Top search terms on intranet — identifies gaps, fears, and information needs | All | Intranet search analytics | Baseline snapshot at launch | Strategy-related terms in top 10 | FAQ terms declining (needs met) | Weekly | Digital Comms
M-019 | Engagement Survey Scores — Next Cycle | Scores on 'strategic direction', 'leadership communication', and 'change management' in next annual engagement survey | All | Annual engagement survey | Previous survey scores | +5% on target questions | +10% on target questions | Annual (next cycle) | CHRO

## Leading Indicators
Leading Indicators — Early Warning System
Indicator ID | Indicator | What It Signals | Audience | Data Source | Alert Threshold | Response Action | Owner
LI-001 | Spike in 'layoffs', 'job security', or 'redundancy' internal search terms | Employee fear and anxiety about job security; narrative not landing as intended | All | Intranet search analytics | 20%+ week-over-week increase in these search terms | Immediately update FAQ with direct job security messaging; deploy manager talking points; consider executive video message | Comms Lead
LI-002 | Manager meeting completion rate below 60% at end of Week 1 | Manager resistance, scheduling barriers, or lack of enablement — risk of message vacuum | Managers | Manager reporting / HR system | < 60% completion by end of Day 7 | Escalate to VP HR and department heads; deploy reminder and support pack; offer 1:1 coaching to struggling managers | HR Lead
LI-003 | Executive email open rate below 50% | Disengagement from leadership communications; employees may be tuning out | Corporate | Email platform analytics | < 50% open rate on any send | Deploy follow-up via alternative channel (Teams, Intranet banner, manager cascade); review subject line and send timing | Comms Lead
LI-004 | Spike in HR inquiries related to restructuring, role changes, or org design | Narrative failure — employees not getting answers through official channels; fear escalating | All | HR inquiry tracking (HR case management system) | 25%+ increase in restructuring-related inquiries week-over-week | Deploy targeted clarification messaging; update FAQ; brief HR partners with holding statements; escalate to leadership if sustained | HR Lead
LI-005 | Decline in intranet hub return visits (repeat visitors dropping) | Content is not resonating or updating frequently enough to drive ongoing engagement | All | Intranet analytics | Return visitor rate drops below 30% in Week 2+ | Refresh hub with team-specific stories, manager spotlights, and Q&A responses; add new content weekly | Digital Comms
LI-006 | Manager feedback forms indicate inability to answer team questions | Training gap — managers not sufficiently equipped to handle Q&A | Managers | Manager feedback form (post-session) | 30%+ of managers report difficulty answering questions | Deploy supplemental manager briefing document within 24 hours; schedule group Q&A call with senior leader; update FAQ | HR Lead / L&D Lead
LI-007 | Social media / Blind platform sentiment tracking negative themes | External reputation risk; internal concerns leaking publicly; talent brand damage | All (external signal) | Blind, LinkedIn, Glassdoor, social listening tools | Any sustained (3+ days) negative theme tied to the announcement | Activate external comms protocol; review internal messaging gaps; consider proactive employer brand response | Comms Lead / PR
LI-008 | Attrition intent survey spike (10%+ above baseline) | Retention crisis emerging — employees actively considering leaving as a result of comms | All | Pulse survey / attrition intent question | Attrition intent 10%+ above pre-announcement baseline | Escalate immediately to CHRO; activate retention risk protocol; deploy personalised manager conversations; review comp and role clarity messaging | CHRO
LI-009 | Frontline shift briefings not completed or poorly attended | Frontline employees receiving no comms — risk of rumour mill and misinformation | Frontline | Ops manager reporting / attendance records | < 50% of shifts receive briefing in Week 1 | Escalate to Operations Director; deploy printed briefing cards and digital posters; adjust briefing format to fit shift patterns | Ops Comms
LI-010 | Low FAQ page engagement despite high hub traffic | Employees visiting hub but not finding answers — content architecture or relevance issue | All | Intranet analytics (hub vs FAQ click-through) | FAQ click-through below 20% of hub visitors | Redesign hub navigation to surface FAQ more prominently; add 'top questions this week' widget; review FAQ content relevance | Digital Comms
LI-011 | Decline in manager confidence scores between Week 1 and Week 2 pulse | Manager support measures not working; increased pressure or confusion post-launch | Managers | Manager pulse survey | Confidence score drops more than 1 point week-over-week | Schedule urgent peer learning session; provide additional talking points; ensure senior leader visibility with manager cohort | HR Lead
LI-012 | High volume of 'Ask Leadership' questions on same topic | Identifies a specific gap in messaging — employees not satisfied with existing content on that topic | All | Ask Leadership submission tool | 5+ questions on same topic within 48 hours | Prioritise published response on intranet within 24 hours; update FAQ; consider brief video response from relevant leader | Comms Lead

## Feedback Loops
Feedback Loops — Capturing and Actioning Employee Input
Loop ID | Feedback Mechanism | Frequency | Audience | Input Captured | How Input Is Used | Escalation Path | Owner
FL-001 | Post-Meeting Pulse Survey | After each manager-led team session (Week 1 and Week 2) | All Employees | Clarity of message, Q&A satisfaction, sentiment score, open-text concerns | Themes fed into next manager briefing pack; unresolved questions added to FAQ; Comms team updates messaging where gaps identified | If >30% negative sentiment: escalate to HR Lead and Comms Lead within 24 hours | HR Lead
FL-002 | Intranet Comment and Reaction Tracking | Real-time / reviewed weekly | All Employees | Reactions (likes, helpful, confused), comments, shares, content save rates | Content team reviews weekly; negative reactions or confusion comments trigger content update within 48 hours | Sustained negative reaction pattern: escalate to Comms Lead; offensive comments: escalate to HR | Digital Comms
FL-003 | Manager Feedback Form (Post-Discussion) | Weekly during rollout (Weeks 1–4) | People Managers | Questions they couldn't answer, team mood assessment, support needs, timing issues | Aggregated and sent to Comms Lead and HR Lead weekly; informs next manager briefing and FAQ updates | If >25% managers flagging same concern: convene urgent manager Q&A call within 48 hours | HR Lead
FL-004 | Monthly Employee Sentiment Pulse | Monthly (months 1–3 post-launch) | All Employees | Understanding, confidence, trust, alignment scores (quantitative); open-text concerns (qualitative) | Results shared with senior leadership within 5 business days; comms strategy adjusted based on trends; fed into Leading Indicators tracker | Any dimension dropping below threshold: immediate Comms Lead and CHRO review; response plan within 1 week | CHRO / HR Lead
FL-005 | Quarterly Engagement Survey Integration | Quarterly (next scheduled cycle) | All Employees | Formal engagement scores on: strategic direction, leadership communication, change management, manager effectiveness | Compared against pre-rollout benchmark; formal report to leadership team; long-term strategy adjustment | Sustained decline in engagement scores: escalate to EXCO; commission independent employee listening sessions | CHRO
FL-006 | 'Ask Leadership' Question Submission Tracking | Ongoing / reviewed weekly | All Employees | Employee questions submitted via intranet or email; volume, themes, and sentiment | Top 5 questions answered publicly on intranet within 5 business days; patterns inform FAQ updates and future comms content | High volume on single topic (5+ in 48 hours): immediate FAQ update and leadership response required | Comms Lead
FL-007 | HR Inquiry Categorisation and Trending | Weekly (throughout rollout period) | All Employees | Volume and category of HR queries (restructuring, role clarity, AI impact, benefits, attrition intent) | Weekly HR dashboard shared with CHRO; spikes trigger comms response; holding statements updated based on top inquiry themes | 25%+ spike in restructuring queries: trigger Comms Lead / CHRO review; activate narrative-clarification response plan | HR Lead
FL-008 | Executive Listening Session Summaries | Bi-weekly (first 6 weeks), then monthly | Representative Employee Groups | Qualitative themes from small-group sessions with senior leaders; unfiltered employee voice | Verbatim themes shared with EXCO (anonymised); directly informs leadership communication tone and content | Themes suggesting fundamental trust breakdown or morale crisis: immediate EXCO escalation and response session required | CHRO / Comms Lead

## Rollout Tracker
Rollout Tracker — 2-Week Communications Activity Plan
Week | Day | Activity | Channel | Audience | Status | Owner | Notes
Week 1 | Mon Day 1 | Executive all-company email — strategic direction announcement | Email (Outlook) | All Employees | Planned | Comms Lead | Subject line pre-tested with employee panel; personalised by CEO
Week 1 | Mon Day 1 | Intranet leadership strategy hub — go-live | Intranet (SharePoint) | All Employees | Planned | Digital Comms | Hub includes: overview, FAQ, video, manager toolkit, Q&A submission
Week 1 | Mon Day 1 | Manager briefing pack distributed (email + Teams) | Email / Microsoft Teams | People Managers | Planned | HR Lead | Pack includes: talking points, FAQ, briefing guide, pulse survey link
Week 1 | Tue Day 2 | Manager team briefing sessions begin (all teams) | In-person / virtual team meetings | All Employees | Planned | People Managers | Managers use briefing pack; completion tracked via reporting form
Week 1 | Tue Day 2 | Frontline shift briefings begin (operations) | In-person shift briefing / printed cards | Frontline | Planned | Ops Comms | Shift supervisor-led; printed one-pager provided for all shifts
Week 1 | Wed Day 3 | Post-meeting pulse survey deployed (employees) | Pulse survey platform | All Employees | Planned | HR Lead | 5-question survey sent to all employees who attended a team briefing
Week 1 | Wed Day 3 | Manager coaching programme — cohort 1 session | Virtual (Teams/Zoom) | People Managers | Planned | L&D Lead | 1-hour live session: handling tough Q&A, reading team sentiment
Week 1 | Thu Day 4 | 'Ask Leadership' Q&A channel — first response batch published | Intranet hub | All Employees | Planned | Comms Lead | Top 10 questions answered; published within 72 hours of launch
Week 1 | Thu Day 4 | HR inquiry categorisation — first weekly review | HR case management system | HR Team | Planned | HR Lead | Identify top themes; brief CHRO; update holding statements if needed
Week 1 | Fri Day 5 | Manager feedback form — first submission deadline | Online form (intranet) | People Managers | Planned | HR Lead | Managers submit: questions raised, mood assessment, support gaps
Week 1 | Fri Day 5 | Week 1 leading indicators review — Comms & HR team | Internal meeting (Teams) | Comms & HR Teams | Planned | Comms Lead | Review: open rates, hub traffic, FAQ engagement, search trends, pulse survey results
Week 1 | Fri Day 5 | Intranet hub content update — refresh with week 1 Q&A themes | Intranet (SharePoint) | All Employees | Planned | Digital Comms | Add top Q&As from week; update FAQ with any unanticipated questions
Week 2 | Mon Day 8 | Follow-up email to non-openers — corporate segment | Email (Outlook) | Corporate (non-openers) | Planned | Comms Lead | Shortened version; different subject line; include direct hub link
Week 2 | Mon Day 8 | Manager coaching programme — cohort 2 session | Virtual (Teams/Zoom) | People Managers | Planned | L&D Lead | Focus on managers who flagged difficulty in Week 1 feedback form
Week 2 | Tue Day 9 | Executive listening session — Cohort 1 (Corporate) | Virtual small-group session | Corporate Employees (sample) | Planned | CHRO | 15–20 employees; CEO or senior leader hosts; themes captured and shared
Week 2 | Tue Day 9 | Frontline shift briefings — completion check and catch-up | In-person / printed materials | Frontline | Planned | Ops Comms | Any missed shifts from Week 1 completed; updated Q&A cards distributed
Week 2 | Wed Day 10 | Monthly sentiment pulse survey launch | Pulse survey platform | All Employees | Planned | HR Lead | Includes: understanding, confidence, trust, and eNPS question
Week 2 | Wed Day 10 | Social media / Blind sentiment review | Social listening tool / manual review | Comms Lead | Planned | Comms Lead | Check for negative themes related to announcement; flag to PR if needed
Week 2 | Thu Day 11 | FAQ page update — second batch based on 'Ask Leadership' submissions | Intranet (SharePoint) | All Employees | Planned | Digital Comms | Prioritise any topics with 3+ submissions; tag manager-specific topics
Week 2 | Thu Day 11 | HR inquiry trending report — shared with CHRO and Comms Lead | Internal report (email) | CHRO / Comms Lead | Planned | HR Lead | 2-week trend vs launch baseline; flag any emerging risk themes
Week 2 | Fri Day 12 | Manager feedback form — Week 2 submission deadline | Online form (intranet) | People Managers | Planned | HR Lead | Assess improvement vs Week 1; identify persistent gaps
Week 2 | Fri Day 12 | 2-week rollout retrospective — Comms, HR, and Ops teams | In-person / virtual meeting | Comms & HR & Ops Teams | Planned | Comms Lead | Review all leading indicators, pulse results, and feedback; agree 30-day plan adjustments
Week 2 | Fri Day 12 | 30-day plan confirmed and communicated to stakeholders | Email / Teams | Senior Leadership | Planned | Comms Lead | Summary of 2-week results, metrics status, and adjusted 30-day approach

## Risk Register
Risk Register — Communications Plan Risks and Mitigations
Risk ID | Risk Description | Likelihood (H/M/L) | Impact (H/M/L) | Risk Score | Mitigation Strategy | Owner | Status
R-001 | Employees interpret 'startup culture' messaging as a signal of impending layoffs or role changes | H | H | High | Pre-emptive FAQ with explicit job security messaging; manager talking points addressing this directly; review all copy before send | Comms Lead | Active
R-002 | Manager burnout prevents effective and consistent message delivery to teams | H | H | High | Manager support package with ready-to-use materials; reduce meeting admin burden; coaching programme; peer support groups | HR Lead | Active
R-003 | Frontline employees do not receive or engage with corporate communications due to shift patterns and screen access | M | H | High | Multi-channel distribution (printed, digital screens, shift briefings); shift-friendly formats; ops manager accountability | Ops Comms | Active
R-004 | AI and automation messaging triggers widespread job security anxiety across all employee groups | H | M | Medium | Specific AI FAQ section with career development commitments; avoid jargon; include concrete role protection language | Comms Lead | Active
R-005 | Executive email is perceived as tone-deaf, out-of-touch, or insufficiently empathetic | M | H | High | Pre-test email copy with diverse employee panels; include personal and empathetic framing; avoid corporate-speak | Comms Lead | Active
R-006 | Feedback loops fail to surface genuine employee concerns due to low trust or fear of visibility | M | M | Medium | Ensure anonymous feedback channels; train managers to encourage honest input; communicate how feedback is used | HR Lead | Active
R-007 | Inconsistent message delivery across managers creates confusion and contradictory narratives | M | H | High | Single-source briefing pack with locked key messages; cascade check-in call before sessions begin; manager Q&A hotline | HR Lead / Comms Lead | Active
R-008 | Communications plan does not reach or land with geographically dispersed or remote employees | M | M | Medium | Ensure digital-first channels; regional manager cascade; intranet hub accessible globally; translated materials if needed | Digital Comms | Active
R-009 | Negative sentiment leaks externally via Blind, social media, or press — reputational damage | L | H | Medium | Social listening activated day 1; PR on standby for reactive response; ensure internal comms is sufficiently reassuring | Comms Lead / PR | Active
R-010 | Leadership team is not aligned on key messages — contradictions emerge in skip-level or direct interactions | L | H | Medium | Pre-launch leadership alignment session; single-source messaging document; Comms Lead approves all executive communications | Comms Lead | Active
Risk Score Legend: HIGH = High Likelihood × High or Medium Impact ¦ MEDIUM = Medium Likelihood × Medium/High Impact or High Likelihood × Low Impact ¦ LOW = Low Likelihood × Low Impact